## Project Tracker
Project ID | Project Name | Project Manager | Department | Status | Priority | Start Date | End Date | Budget (USD) | Actual Spend (USD) | Budget Utilization (%) | Current Sprint | Sprint Velocity | Tasks Total | Tasks Completed | Task Completion (%) | Risk Level | Risk Description | Resource Count | Milestone
PRJ-001 | AI Chat Platform | Alice Chen | Product | On Track | High | 2025-01-06 | 2025-06-30 | 850000 | 420000 |  | 5 | 42 | 120 | 68 |  | Low | No critical blockers | 8 | Beta Launch May 2025
PRJ-002 | ERP Migration | Brian Wu | IT | At Risk | Critical | 2024-11-01 | 2025-08-31 | 1200000 | 890000 |  | 7 | 28 | 200 | 105 |  | High | Legacy data mapping delays | 12 | Data Cutover Jun 2025
PRJ-003 | Mobile App v3 | Cathy Sun | Engineering | On Track | High | 2025-02-03 | 2025-07-31 | 620000 | 280000 |  | 4 | 38 | 90 | 52 |  | Medium | iOS App Store review risk | 6 | App Store Submission Jun 2025
PRJ-004 | Data Warehouse | David Li | Data | Delayed | High | 2024-12-02 | 2025-09-30 | 950000 | 720000 |  | 8 | 22 | 160 | 88 |  | High | Infrastructure provisioning lag | 10 | Prod Go-Live Aug 2025
PRJ-005 | Brand Refresh | Emily Zhang | Marketing | Completed | Medium | 2025-01-13 | 2025-04-30 | 180000 | 175000 |  | 10 | 30 | 60 | 60 |  | Low | Completed on time | 4 | Launch Apr 2025
PRJ-006 | Security Audit | Frank Liu | Security | On Track | Critical | 2025-03-03 | 2025-06-30 | 320000 | 155000 |  | 3 | 45 | 80 | 44 |  | Medium | Penetration test findings | 5 | Final Report Jun 2025
PRJ-007 | HR Self-Service | Grace Wang | HR | On Track | Medium | 2025-02-10 | 2025-08-29 | 410000 | 195000 |  | 4 | 35 | 100 | 48 |  | Low | Minor scope creep | 7 | UAT Jul 2025
PRJ-008 | Cloud Cost Opt. | Henry Zhao | IT | Completed | Medium | 2025-01-06 | 2025-03-31 | 140000 | 132000 |  | 10 | 40 | 50 | 50 |  | Low | Completed under budget | 3 | Closed Mar 2025
PRJ-009 | Customer Portal | Iris Xu | Product | At Risk | High | 2025-03-17 | 2025-09-30 | 780000 | 320000 |  | 3 | 25 | 140 | 52 |  | High | Third-party API dependency | 9 | Public Beta Aug 2025
PRJ-010 | Compliance 2025 | Jack Ma | Legal | On Track | Critical | 2025-01-13 | 2025-12-31 | 560000 | 230000 |  | 5 | 38 | 180 | 85 |  | Medium | Regulatory timeline risk | 8 | Audit Submission Oct 2025
PRJ-011 | Sales Dashboard | Karen Chen | Sales | Completed | Low | 2025-01-06 | 2025-03-31 | 95000 | 91000 |  | 10 | 32 | 40 | 40 |  | Low | Delivered on schedule | 3 | Go-Live Mar 2025
PRJ-012 | API Gateway v2 | Leo Wang | Engineering | On Track | High | 2025-02-24 | 2025-07-31 | 430000 | 188000 |  | 4 | 44 | 85 | 44 |  | Low | Performance testing pending | 5 | Load Test Jun 2025
PRJ-013 | Supply Chain BI | Mia Liu | Operations | Delayed | High | 2024-12-09 | 2025-10-31 | 870000 | 650000 |  | 9 | 20 | 155 | 82 |  | High | Data source integration issues | 11 | Dashboard Handoff Sep 2025
PRJ-014 | Talent Mgmt 2.0 | Nina Park | HR | On Track | Medium | 2025-04-07 | 2025-11-28 | 370000 | 95000 |  | 2 | 36 | 90 | 24 |  | Low | On schedule | 6 | Pilot Oct 2025
PRJ-015 | Finance Close | Owen Xu | Finance | On Track | Critical | 2025-01-06 | 2025-06-30 | 290000 | 178000 |  | 5 | 42 | 70 | 48 |  | Medium | Month-end dependency | 4 | Go-Live Jun 2025
PRJ-016 | IoT Sensor Grid | Paul Zhang | R&D | At Risk | High | 2025-02-03 | 2025-12-31 | 1100000 | 485000 |  | 4 | 18 | 200 | 78 |  | High | Hardware supply shortage | 14 | Field Pilot Oct 2025
PRJ-017 | Content CMS | Quinn Li | Marketing | Completed | Low | 2025-02-17 | 2025-05-09 | 130000 | 128000 |  | 10 | 28 | 50 | 50 |  | Low | Delivered 2 days early | 3 | Launch May 2025
PRJ-018 | Chatbot v2 | Rachel Sun | Customer Svc | On Track | Medium | 2025-03-10 | 2025-08-29 | 350000 | 140000 |  | 3 | 34 | 75 | 30 |  | Medium | NLP model accuracy | 5 | Rollout Aug 2025
PRJ-019 | Partner Ecosystem | Steve Chen | Partnerships | Delayed | Medium | 2025-01-20 | 2025-09-30 | 480000 | 380000 |  | 7 | 24 | 110 | 65 |  | Medium | Partner onboarding slow | 7 | Integration Sprint Sep 2025
PRJ-020 | BI Modernization | Tina Wu | Data | On Track | High | 2025-03-03 | 2026-02-27 | 1350000 | 210000 |  | 2 | 40 | 240 | 48 |  | Low | Well-resourced | 16 | Phase 1 Go-Live Sep 2025
PRJ-021 | DevSecOps Pipeline | Uma Zhou | DevOps | On Track | High | 2025-02-10 | 2025-08-01 | 395000 | 210000 |  | 4 | 46 | 80 | 44 |  | Low | CI/CD stable | 5 | Full Rollout Jul 2025
PRJ-022 | Retail Analytics | Victor Li | Analytics | At Risk | High | 2025-01-13 | 2025-09-30 | 730000 | 510000 |  | 8 | 22 | 160 | 90 |  | High | Replatform risk mid-project | 9 | Store Rollout Aug 2025
PRJ-023 | Employee App | Wendy Ma | HR | On Track | Low | 2025-03-17 | 2025-10-31 | 280000 | 88000 |  | 2 | 32 | 70 | 22 |  | Low | Good team velocity | 4 | Beta Sep 2025
PRJ-024 | Pricing Engine | Xavier Xu | Product | On Track | High | 2025-02-24 | 2025-08-29 | 560000 | 245000 |  | 4 | 38 | 100 | 48 |  | Medium | A/B test infra needed | 7 | Launch Aug 2025
PRJ-025 | Network Upgrade | Yara Chen | IT | Completed | Critical | 2025-01-06 | 2025-04-30 | 720000 | 698000 |  | 10 | 30 | 90 | 90 |  | Low | Completed on time | 8 | Closed Apr 2025
PRJ-026 | Legal Workflow | Zach Liu | Legal | On Track | Medium | 2025-04-07 | 2025-10-31 | 210000 | 55000 |  | 2 | 36 | 60 | 18 |  | Low | Early stage, on track | 3 | UAT Sep 2025
PRJ-027 | Predictive Maint. | Alice Chen | R&D | Delayed | High | 2024-11-01 | 2025-12-31 | 990000 | 780000 |  | 9 | 16 | 180 | 95 |  | High | Model retraining loops | 12 | Prod Deployment Nov 2025
PRJ-028 | Customer 360 | Brian Wu | CRM | On Track | High | 2025-03-03 | 2025-11-28 | 670000 | 180000 |  | 3 | 40 | 130 | 42 |  | Medium | Data quality cleanup | 8 | Integration Go-Live Oct 2025
PRJ-029 | Warehouse Robotics | Cathy Sun | Operations | At Risk | Critical | 2025-02-03 | 2025-12-31 | 2100000 | 980000 |  | 5 | 20 | 300 | 120 |  | High | Robot firmware delays | 18 | Pilot Deployment Nov 2025
PRJ-030 | Finance Reporting | David Li | Finance | Completed | Medium | 2025-01-06 | 2025-03-28 | 160000 | 158000 |  | 10 | 35 | 45 | 45 |  | Low | Delivered on time | 3 | Closed Mar 2025

## Summary
Metric | Value
Total Projects
On Track
At Risk
Delayed
Completed
Total Budget (USD)
Total Actual Spend (USD)
Overall Budget Utilization (%)
Avg Sprint Velocity
Avg Task Completion (%)
High Risk Projects